## Dashboard
RED TEAM MASTERY — PROGRESS DASHBOARD
From intermediate pentester to elite adversary-emulation operator
TASKS DONE | XP EARNED | TOTAL XP | % COMPLETE
LEVEL | RANK
PROGRESS BY PHASE
Phase | Tasks Done | Task Count | XP Earned | XP Total
Phase 1
Phase 2
Phase 3
Phase 4
Phase 5
Phase 6
Tracks
Capstone
PROGRESS BY TRACK
Track | Tasks Done | Task Count | XP Earned | XP Total
Core
Technical
Tradecraft
Reporting
Detection
Purple
How to use: mark Status = 'Done' on the Roadmap tab. Earned XP, level, rank and all charts update automatically.

## Roadmap
ID | Phase | Track | Category | Task | Difficulty | XP | Status | Earned XP | Date Done | Notes
P1-01 | Phase 1 | Core | Learn | Windows internals primitives: processes/threads, tokens & impersonation, integrity levels, UAC, LSASS, DPAPI, PPL | ★★★ | 120 | Not Started
P1-02 | Phase 1 | Detection | Learn | Windows telemetry map: Security/Sysmon events, ETW, AMSI, WLDP, kernel callbacks (conceptual) | ★★★ | 120 | Not Started
P1-03 | Phase 1 | Technical | Learn | PowerShell & .NET tooling fluency (read AND write tooling, not one-liners) | ★★ | 100 | Not Started
P1-04 | Phase 1 | Technical | Learn | C# read-fluency + C basics: pointers, structs, calling conventions (Phase 3 gate) | ★★★ | 150 | Not Started
P1-05 | Phase 1 | Core | Learn | AD 101 done properly: domain/forest/trusts, Kerberos vs NTLM, LDAP, GPO, DNS | ★★★ | 120 | Not Started
P1-06 | Phase 1 | Core | Lab | Build hypervisor lab: DC + 2-3 workstations + Linux box, snapshots enabled | ★★ | 250 | Not Started
P1-07 | Phase 1 | Detection | Lab | Install Sysmon (SwiftOnSecurity config) + ship logs to Wazuh/Elastic SIEM | ★★★ | 200 | Not Started
P1-08 | Phase 1 | Core | Lab | Provision GOAD; map with BloodHound; explain every edge in English | ★★★ | 250 | Not Started
P1-09 | Phase 1 | Core | Exercise | Dump & diff process tokens; escalate integrity level manually | ★★ | 100 | Not Started
P1-10 | Phase 1 | Detection | Exercise | Trigger AMSI on a known-bad string; watch the event fire in your SIEM | ★★ | 100 | Not Started
P1-11 | Phase 1 | Technical | Exercise | Write a C# tool that lists processes via P/Invoke (not System.Diagnostics) | ★★★ | 150 | Not Started
P1-12 | Phase 1 | Core | Assessment | GATE: Explain Kerberos TGT/TGS exchange + where each attack plugs in (no notes) | ★★★ | 300 | Not Started
P1-13 | Phase 1 | Core | Assessment | GATE: Read your own SIEM events + compile your own P/Invoke tool | ★★★ | 300 | Not Started
P2-01 | Phase 2 | Core | Learn | Discovery: SharpHound/BloodHound, LDAP recon, GPO/ACL enumeration, session hunting | ★★★ | 120 | Not Started
P2-02 | Phase 2 | Core | Learn | Credential access: Kerberoast, AS-REP roast, DCSync, LSASS/DPAPI/SAM extraction | ★★★★ | 150 | Not Started
P2-03 | Phase 2 | Core | Learn | Priv-esc: ACL abuse (GenericAll/WriteDACL), constrained/unconstrained/RBCD delegation, GPO abuse | ★★★★ | 150 | Not Started
P2-04 | Phase 2 | Core | Learn | ADCS ESC1-ESC14 certificate attack family (know these cold) | ★★★★★ | 250 | Not Started
P2-05 | Phase 2 | Core | Learn | Lateral movement: PtH, PtT, overpass-the-hash, WMI/WinRM/PsExec/SMB/DCOM exec | ★★★ | 150 | Not Started
P2-06 | Phase 2 | Core | Learn | Persistence: Golden/Silver/Diamond tickets, AdminSDHolder, DCSync rights, cert persistence | ★★★★ | 150 | Not Started
P2-07 | Phase 2 | Core | Learn | Trusts: intra/cross-forest attack paths, SID history, trust key abuse | ★★★★ | 150 | Not Started
P2-08 | Phase 2 | Detection | Lab | GOAD full chain (foothold->roast->ACL->DCSync) WHILE SIEM records, then write the detections | ★★★★ | 350 | Not Started
P2-09 | Phase 2 | Core | Lab | HTB Pro Lab: Dante (methodology warm-up) | ★★ | 300 | Not Started
P2-10 | Phase 2 | Core | Lab | HTB Pro Lab: Zephyr (intermediate AD red-team sim) | ★★★★ | 400 | Not Started
P2-11 | Phase 2 | Core | Exercise | Execute one ADCS ESC path (ESC1 or ESC8) end-to-end with Certipy | ★★★★ | 200 | Not Started
P2-12 | Phase 2 | Core | Exercise | Cross-forest compromise via trust abuse | ★★★★ | 200 | Not Started
P2-13 | Phase 2 | Core | Exercise | Complete a full lab with NO Metasploit and NO mimikatz easy button (Rubeus/Certipy/impacket) | ★★★★ | 250 | Not Started
P2-14 | Phase 2 | Core | Assessment | Own a fresh unseen AD lab UNASSISTED + produce path diagram + remediation | ★★★★★ | 400 | Not Started
P2-15 | Phase 2 | Core | Milestone | MILESTONE: Pass CRTP (Altered Security) | ★★★★★ | 800 | Not Started
P3-01 | Phase 3 | Tradecraft | Learn | C2 architecture & operation: listeners, stagers, sleep/jitter, malleable profiles, redirectors, egress, OPSEC | ★★★★ | 150 | Not Started
P3-02 | Phase 3 | Technical | Learn | Payload dev: shellcode loaders, injection family (classic/APC/thread-hijack/hollowing/module-stomp/early-bird) | ★★★★ | 200 | Not Started
P3-03 | Phase 3 | Technical | Learn | Windows API for offense + direct/indirect syscalls (why they exist as evasion) | ★★★★ | 200 | Not Started
P3-04 | Phase 3 | Tradecraft | Learn | Redirector infrastructure as code (Terraform/Ansible), TLS, categorization, mail/web redirectors | ★★★ | 150 | Not Started
P3-05 | Phase 3 | Tradecraft | Track | Master a commercial-grade C2: Cobalt Strike end-to-end | ★★★★ | 250 | Not Started
P3-06 | Phase 3 | Tradecraft | Track | Master an open C2: Sliver / Mythic / Havoc | ★★★ | 200 | Not Started
P3-07 | Phase 3 | Technical | Exercise | Write a shellcode loader in C# AND in C that runs a benign beacon in lab | ★★★★ | 250 | Not Started
P3-08 | Phase 3 | Tradecraft | Exercise | Stand up HTTP + DNS redirector infra with Terraform; run an op through it | ★★★★ | 200 | Not Started
P3-09 | Phase 3 | Detection | Exercise | Author a malleable C2 profile; verify how it changes your network signature in SIEM | ★★★ | 200 | Not Started
P3-10 | Phase 3 | Detection | Exercise | Implement 3 injection techniques; compare Sysmon/ETW footprint of each | ★★★★ | 200 | Not Started
P3-11 | Phase 3 | Technical | Track | Sektor7 RED TEAM Operator: Malware Development Essentials | ★★★ | 300 | Not Started
P3-12 | Phase 3 | Technical | Track | MalDev Academy core modules (loaders, injection, evasion) | ★★★★ | 300 | Not Started
P3-13 | Phase 3 | Technical | Assessment | Custom loader YOU wrote beats default-config Defender in lab (explain why each evasion works) | ★★★★★ | 400 | Not Started
P3-14 | Phase 3 | Tradecraft | Milestone | MILESTONE: Pass CRTO (Zero-Point Security) | ★★★★★ | 800 | Not Started
P4-01 | Phase 4 | Technical | Learn | AMSI bypass concepts (patching, provider abuse) + the detection for each | ★★★★ | 180 | Not Started
P4-02 | Phase 4 | Technical | Learn | ETW tamper/blinding concepts and their trade-offs (increasingly detected) | ★★★★ | 180 | Not Started
P4-03 | Phase 4 | Technical | Learn | Userland unhooking, direct/indirect syscalls, call-stack spoofing, sleep-mask/heap encryption | ★★★★★ | 250 | Not Started
P4-04 | Phase 4 | Technical | Learn | PPL / LSASS protection & Credential Guard implications | ★★★★ | 180 | Not Started
P4-05 | Phase 4 | Detection | Learn | EDR telemetry model: kernel callbacks, minifilters, ETW-TI (what an EDR actually sees) | ★★★★★ | 200 | Not Started
P4-06 | Phase 4 | Detection | Learn | Detection engineering: write Sigma rules, ATT&CK mapping, detections in Elastic/Splunk | ★★★★ | 200 | Not Started
P4-07 | Phase 4 | Detection | Lab | Deploy a real EDR in lab (Elastic Defend/MDE eval); iterate loaders against it | ★★★★★ | 400 | Not Started
P4-08 | Phase 4 | Purple | Lab | DetectionLab / SimuLand / Splunk Attack Range: paired attack + detect | ★★★★ | 300 | Not Started
P4-09 | Phase 4 | Purple | Lab | MITRE Caldera + Atomic Red Team: run technique, observe telemetry, tune detection | ★★★★ | 300 | Not Started
P4-10 | Phase 4 | Purple | Exercise | Evade->re-detect loop x5: evade Defender, then write the Sigma/EDR rule that re-catches it | ★★★★★ | 350 | Not Started
P4-11 | Phase 4 | Tradecraft | Exercise | Build a 'telemetry budget' doc: every emitted signal in a full chain + mitigation | ★★★★ | 200 | Not Started
P4-12 | Phase 4 | Detection | Assessment | Custom implant survives a REAL EDR during a multi-step chain + hand over a detection pack | ★★★★★ | 500 | Not Started
P4-13 | Phase 4 | Technical | Milestone | MILESTONE (optional): Pass OffSec OSEP (PEN-300) | ★★★★★ | 800 | Not Started
P5-01 | Phase 5 | Core | Learn | Entra ID: OAuth/OIDC, tokens (PRT!), conditional access, app regs/service principals, consent phishing, device code | ★★★★ | 200 | Not Started
P5-02 | Phase 5 | Core | Learn | Hybrid identity: Entra Connect, PHS/PTA/federation attack paths | ★★★★★ | 200 | Not Started
P5-03 | Phase 5 | Core | Learn | On-prem <-> cloud pivots: ADFS/PRT abuse, Intune/GPO, synced creds, seamless SSO | ★★★★★ | 200 | Not Started
P5-04 | Phase 5 | Technical | Learn | AWS: IAM priv-esc paths, role assumption, metadata/SSRF-to-creds, Pacu methodology | ★★★★ | 180 | Not Started
P5-05 | Phase 5 | Technical | Learn | GCP IAM/service accounts + containers/K8s as pivot surface (RBAC, SA tokens, escapes) | ★★★ | 150 | Not Started
P5-06 | Phase 5 | Technical | Lab | CloudGoat (AWS) scenario end-to-end with written attack path | ★★★ | 300 | Not Started
P5-07 | Phase 5 | Core | Lab | AzureGoat / PurpleCloud tenant scenario | ★★★★ | 300 | Not Started
P5-08 | Phase 5 | Core | Exercise | Consent-phish -> token -> Graph enumeration -> privilege path in a lab tenant | ★★★★ | 250 | Not Started
P5-09 | Phase 5 | Core | Exercise | Compromise on-prem, harvest synced creds / PRT, pivot to cloud (and reverse) | ★★★★★ | 300 | Not Started
P5-10 | Phase 5 | Core | Assessment | Own a HYBRID lab (Entra + Connect + on-prem AD); boundary-crossing chain BOTH directions | ★★★★★ | 500 | Not Started
P5-11 | Phase 5 | Core | Milestone | MILESTONE (optional): Pass CARTP (Altered Security Azure red team) | ★★★★★ | 700 | Not Started
P6-01 | Phase 6 | Core | Learn | CTI -> ATT&CK emulation pipeline: consume a report, extract TTPs, build an emulation plan with safe substitutes | ★★★★★ | 250 | Not Started
P6-02 | Phase 6 | Core | Learn | MITRE Adversary Emulation Library plans (APT29, FIN7, menuPass): run and adapt | ★★★★ | 200 | Not Started
P6-03 | Phase 6 | Reporting | Learn | Engagement leadership: scoping, RoE, deconfliction, evidence handling, crown-jewel analysis, objective-based success | ★★★★ | 250 | Not Started
P6-04 | Phase 6 | Purple | Learn | Purple-team facilitation: run a detection-tuning cycle as a collaborative exercise | ★★★★ | 200 | Not Started
P6-05 | Phase 6 | Core | Exercise | Run an APT29 or FIN7 emulation plan in Caldera against instrumented defenses | ★★★★★ | 350 | Not Started
P6-06 | Phase 6 | Purple | Exercise | Track detection coverage across an engagement in Vectr | ★★★ | 200 | Not Started
P6-07 | Phase 6 | Core | Milestone | MILESTONE: Pass CRTL (Certified Red Team Lead) | ★★★★★ | 900 | Not Started
TR-01 | Tracks | Technical | Track | Vuln research: write ONE from-scratch memory-corruption exploit in a lab | ★★★★★ | 400 | Not Started
TR-02 | Tracks | Technical | Track | Reproduce a CVE from a public writeup / N-day weaponization | ★★★★ | 250 | Not Started
TR-03 | Tracks | Tradecraft | Track | Build redirector hygiene + attribution kit (tooling matched to emulated actor) | ★★★★ | 250 | Not Started
TR-04 | Tracks | Tradecraft | Track | Author deconfliction, data-handling, cleanup & kill-switch procedures | ★★★ | 200 | Not Started
TR-05 | Tracks | Reporting | Track | Write BOTH an executive narrative + a technical report for a major lab | ★★★★ | 300 | Not Started
TR-06 | Tracks | Detection | Track | Maintain a personal TTP <-> telemetry notebook (every technique -> its detection) | ★★★ | 200 | Not Started
TR-07 | Tracks | Purple | Track | Run a documented attack->detect->evade->re-detect cycle with a blue teammate | ★★★★ | 300 | Not Started
CAP-1 | Capstone | Core | Capstone | CAP-1: Assumed-breach unseen AD lab -> Domain Admin unassisted + path diagram + report + detections | ★★★★ | 1000 | Not Started
CAP-2 | Capstone | Tradecraft | Capstone | CAP-2: External->internal chain with YOUR loader + C2 through redirectors; survive default Defender + OPSEC notes | ★★★★★ | 1200 | Not Started
CAP-3 | Capstone | Purple | Capstone | CAP-3: Same objective vs a REAL EDR; deliver red report + blue detection pack + evade<->re-detect coverage | ★★★★★ | 1500 | Not Started
CAP-4 | Capstone | Core | Capstone | CAP-4: Hybrid objective - start in cloud, land on-prem to a crown jewel (or reverse) with conditional access in play | ★★★★★ | 1500 | Not Started
CAP-5A | Capstone | Core | Capstone | CAP-5A: Named-APT emulation #1 - intel-driven plan, execute vs instrumented defenses, exec+technical report + purple debrief | ★★★★★ | 2000 | Not Started
CAP-5B | Capstone | Core | Capstone | CAP-5B: Named-APT emulation #2 - a DIFFERENT actor with different tradecraft; measurably improve detection coverage | ★★★★★ | 2000 | Not Started

## Levels (hidden)
LevelNo | CumulativeXP | RankLvl | RankName
1 | 0 | 1 | Initiate
2 | 255 | 5 | Operator Cadet
3 | 565 | 10 | Journeyman Operator
4 | 930 | 15 | Adversary Emulator
5 | 1350 | 20 | Senior Red Teamer
6 | 1825 | 25 | Red Team Lead
7 | 2355 | 30 | Elite APT Emulation Specialist
8 | 2940
9 | 3580
10 | 4275
11 | 5025
12 | 5830
13 | 6690
14 | 7605
15 | 8575
16 | 9600
17 | 10680
18 | 11815
19 | 13005
20 | 14250
21 | 15550
22 | 16905
23 | 18315
24 | 19780
25 | 21300
26 | 22875
27 | 24505
28 | 26190
29 | 27930
30 | 29725
31 | 31575
32 | 33480
33 | 35440
34 | 37455
35 | 39525
36 | 41650
37 | 43830
38 | 46065
39 | 48355
40 | 50700

## Legend
LEGEND & LEVELING
Categories
Learn | Study/understand a concept or technique family
Exercise | Hands-on drill in your own lab
Lab | Full lab / range / Pro Lab environment
Assessment | Gate you must pass to advance (proves the skill)
Milestone | Certification or major checkpoint
Track | Ongoing parallel-track work (tradecraft, reporting, etc.)
Capstone | Independent end-to-end engagement simulation
Tracks
Core | Main technical attack-chain progression
Technical | Offensive dev, exploit dev, maldev depth
Tradecraft | OPSEC, C2 infra, attribution discipline
Reporting | Executive + technical writing, engagement leadership
Detection | Detection-aware red teaming, Sigma/telemetry
Purple | Purple-team collaboration cycles
Difficulty | 1 star (foundational) to 5 stars (elite)
Leveling | Level up needs 200 + 55 x (level) XP each step; ranks unlock at levels 1/5/10/15/20/25/30